# Roadmap v1

# Roadmap (MVP -> Beta -> GA)

## 1) Timeline Assumptions

1. Team can run discovery and build in parallel.

2. External calendar/AI integrations are available early.

3. Scope control is strict for MVP.

## 2) Phase Plan

## Phase 0: Foundation and Discovery (Weeks 1-3)

1. Finalize requirements and architecture baseline.

2. Validate primary user journeys and assistant confirmation UX.

3. Define security/privacy baselines and data retention defaults.

Exit Criteria:

1. PRD signed off.

2. C4 and data model approved.

3. MVP backlog prioritized with estimates.

## Phase 1: MVP Build (Weeks 4-10)

1. Mobile app shell (voice/text capture, auth, task/event views).

2. Assistant orchestration pipeline (intent, entities, clarification, confirmation).

3. Task service + storage + reminders.

4. Calendar integrations (Google first, then Microsoft, then Apple/CalDAV).

5. Action history and audit logging.

Exit Criteria:

1. End-to-end voice task creation works reliably.

2. At least one calendar provider full read/write working.

3. Confirmation gate enforced for all write operations.

4. Internal alpha passes acceptance criteria in `requirements-v1.md`.

## Phase 2: Private Beta (Weeks 11-14)

1. Scheduling suggestions and ranking improvements.

2. Daily planning and "next best action" quality tuning.

3. Reliability hardening: retries, queue health, sync reconciliation.

4. Observability dashboards and alert thresholds.

Exit Criteria:

1. 20-50 beta users onboarded.

2. Task/action accuracy and reliability meet target thresholds.

3. Critical security and privacy checks pass.

## Phase 3: General Availability (Weeks 15-18)

1. UX polish and onboarding improvements.

2. Expanded provider parity and edge-case handling.

3. SLO tracking and incident runbook validation.

4. Public launch readiness and support workflows.

Exit Criteria:

1. Core SLOs stable for 2 consecutive weeks.

2. No P0/P1 open defects.

3. Data export/delete and policy docs production-ready.

## 3) Milestone Map

1. M1 (Week 3): Architecture and PRD lock.

2. M2 (Week 7): Core assistant + tasks alpha.

3. M3 (Week 10): MVP feature complete.

4. M4 (Week 14): Beta complete with quality targets.

5. M5 (Week 18): GA launch.

## 4) Key Risks and Mitigations

1. Provider API inconsistency:

- Mitigation: adapter layer + integration test suite + queue retries.

2. Latency spikes in LLM/speech providers:

- Mitigation: timeouts, fallback models, async follow-up responses.

3. Incorrect assistant actions:

- Mitigation: strict confirmation gate + safer defaults + audit visibility.

4. Scope creep:

- Mitigation: enforce non-goals and phase gate approvals.

5. Calendar sync drift:

- Mitigation: sync cursors, reconciliation jobs, idempotent writes.

## 5) Staffing and Ownership (Draft)

1. Product owner: requirements, prioritization, rollout decisions.

2. Mobile lead: app UX, local cache, notification UX.

3. Backend lead: orchestration, task/calendar services, APIs.

4. Platform/SRE: observability, deployment, reliability.

5. Security lead: threat model, policy, compliance readiness.